## Product Backlog
Product Name: | Mav’s Animal Shelter Software (MASS) | [6 empty] | Complete Fields in Green!!!
Team ID: | Sho's Shelter
| Team Member Name | [5 empty] | Initials | Student ID
Required | Sho Reagan | [5 empty] | SR | 1001925250
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 22 |  |  |  | Total | Total number of features (in column H)
1 | 16 | 6 |  |  | 1 | Total features left at the end of Sprint #1
2 | 14 | 2 |  |  | 2 | Total features left at the end of Sprint #2
3 | 10 | 4 |  |  | 3 | ...and so on
4 | 10 | 0
5 | 10 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
ANIMAL | 1 | 1 |  | 5 | 1 | Finished in Sprint 1 | User | Track the name, gender, and age for all animals | Keep track of guests at our shelter | Need enum for Gender and abstract Animal class with constructor, getters, and toString. Validate that age is not negative else throw an exception.
DOG | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Staff | Create a new dog (or any other family of animals) | Track pets seeking good homes | Need Dog class that extends Animal along with DogBreed enum (may be any animal family, not necessarily Dog).
LANIM | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Staff | Keep a list of animals | See what animals are available | Requires Shelter class with a shelter name and array list of animals. Need to be able to add an animal and access the available animals.
CAT | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Staff | Create and list cats (or 2nd animal family) as well | Put 2nd pet type up for adoption | Very similar to 1st type of pets
MAINWIN | 5 | 2 |  | 3 |  | Finished in Sprint 2 | User | Display a main window with menu | Use the program more easily | Baseline Nim
TOOLBAR | 6 | 2 |  | 2 |  |  | User | Include a toolbar | Click buttons for actions | Baseline Nim; add 2 buttons for inserting the two animal families
ABOUT | 7 | 2 |  | 3 |  |  | User | Include an About dialog for toolbar icons (Help > About) | Avoid legal trouble | Baseline Nim; need icons for the two animal families; use YOUR name
EXIT | 8 | 2 |  | 2 |  |  | User | Exit the main program (File > Quit or x window control) | Quit reliably | Baseline Nim
DOGDIALOG | 9 | 2 |  | 13 | 1 | Finished in Sprint 1 | Staff | Use dialogs to create a new dog or 1st family (Animal > New) | Track pets seeking good homes | May be a series of JOptionPane dialogs or a single unified dialog
CATDIALOG | 10 | 2 |  | 8 | 1 | Finished in Sprint 1 | Staff | Use dialogs to create a new cat or 2nd family (Animal > New) | Track more pets seeking good homes | Similar to 1st
SHOWANIM | 11 | 2 |  | 5 |  | Finished in Sprint 2 | Staff | Display all animals in the main window (Animal > List Available) | See the beloved animals that are current guests of the shelter | Update after every Insert operation (Animal > List Available will be needed when clients are added in a later sprint). May be a label or similar widget in the data area of the main window
SAVE | 12 | 3 |  | 8 |  | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal.save(bw), Dog.save, Cat.save, Shelter.save; Shelter.filename with getter and setter, and Mass.onSaveClick
LOAD | 13 | 3 |  | 8 |  | Finished in Sprint 3 | Manager | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal.Animal(br), Dog.Dog, Cat.Cat, Shelter.Shelter and Mass.onOpenClick; dialog and logic for handling “dirty” data
NEW | 14 | 3 |  | 5 |  | Finished in Sprint 3 | Director | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mass.onNewShelterClick
SAVEF | 15 | 3 |  | 5 |  | Finished in Sprint 3 | Director | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mass.onSaveAsClick, Shelter.setFilename; adding JFileChooser
LOADF | 16 | 3 |  | 3 |  |  | Director | Load the data from a specified file (File > Open) | Work with multiple shelters | Requires adding JFileChooser
GENERIC | 17 | 4 |  | 13 |  |  | Staff | Refactor Add (Animal) dialogs into generic class and add at least one additional family of animals | Quickly add additional animal families to our guest list | Requires generic class for unified dialog to create new animal guests
ITER | 18 | 4 |  | 5 |  |  |  | Refactor to use iterators to access animals from Shelter | Practice iterators (well?) | Replace numAnimals and getAnimal with getAnimalIterator; update all users of those methods
CLIENT | 19 | 4 |  | 8 |  |  | Staff | Create a new client (Client > New) | Track candidate adopters | Requires Mass.onCreateClient; 1 dialog; class Client; Shelter.addClient and fields
LCLIENT | 20 | 4 |  | 5 |  |  | Client | List clients (Client > List) | See which clients are available | Requires Shelter.numClients and client; and Mass.onClientsList
ADOPT | 21 | 5 |  | 13 |  |  | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Shelter.adopted HashMap<Animal, Client>, new dialog
LADOPT | 22 | 5 |  | 8 |  |  | Staff | List adopted animals (Client > List Adopted and Animal > List Adopted) | See which client adopted which animal | Requires 1 dialog to select the client and 1 dialog to select the animal; Mass.onListAdoptedClick
Bonus Features
NANIM |  | 4 | TBD | 5 |  |  | Client | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
PHOTO |  | 4 | TBD | 8 |  |  | Client | See photo and information about an available animal | Decide if it’s right for my family | Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2022-02-22 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-01
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2022-03-01 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-08
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | MAINWIN |  | Finished in Sprint 2
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2022-03-08 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 0 | 4
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2 |  |  | Finish save method | Completed Day 4
3 |  |  | finish save as method | Completed Day 4
4 |  |  | finish new shelter method | Completed Day 4
5 |  |  | finish open shelter method | Completed Day 4
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2022-04-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2022-04-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84