Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after t
This is the MAXIMUM number of bonus points awarded if you successfully and completely implement this feature.

If blank, this feature is REQUIRED. You MAY NOT work on ANY bonus feature until ALL required features have been implemented.

If non-blank, some
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a re
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product Backlog
Product Name:	Mav’s Animal Shelter Software (MASS)					Complete Fields in Green!!!
Team ID:					Product Backlog Burn Chart / Sprints / Features Remaining at end of Sprint

	Team Member Name					Initials	Student ID
Required

Sprint #	Remaining	Completed This Sprint				Comment
0	22				Total	Total number of features (in column H)
1	22	0			1	Total features left at the end of Sprint #1
2	22	0			2	Total features left at the end of Sprint #2
3	22	0			3	...and so on
4	22	0
5	22	0

				Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Bonus	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
ANIMAL	1	1		5			User	Track the name, gender, and age for all animals	Keep track of guests at our shelter	Need enum for Gender and abstract Animal class with constructor, getters, and toString. Validate that age is not negative else throw an exception.
DOG	2	1		8			Staff	Create a new dog (or any other family of animals)	Track pets seeking good homes	Need Dog class that extends Animal along with DogBreed enum (may be any animal family, not necessarily Dog).
LANIM	3	1		8			Staff	Keep a list of animals	See what animals are available	Requires Shelter class with a shelter name and array list of animals. Need to be able to add an animal and access the available animals.
CAT	4	1		5	1		Staff	Create and list cats (or 2nd animal family) as well	Put 2nd pet type up for adoption	Very similar to 1st type of pets
MAINWIN	5	2		3			User	Display a main window with menu	Use the program more easily	Baseline Nim
TOOLBAR	6	2		2			User	Include a toolbar	Click buttons for actions	Baseline Nim; add 2 buttons for inserting the two animal families
ABOUT	7	2		3			User	Include an About dialog for toolbar icons (Help > About)	Avoid legal trouble	Baseline Nim; need icons for the two animal families; use YOUR name
EXIT	8	2		2			User	Exit the main program (File > Quit or x window control)	Quit reliably	Baseline Nim
DOGDIALOG	9	2		13			Staff	Use dialogs to create a new dog or 1st family (Animal > New Dog)	Track pets seeking good homes	May be a series of JOptionPane dialogs or a single unified dialog
CATDIALOG	10	2		8			Staff	Use dialogs to create a new cat or 2nd family (Animal > New Cat)	Track more pets seeking good homes	Similar to 1st
SHOWANIM	11	2		5			Staff	Display all animals in the main window (Animal > List Available)	See the beloved animals that are current guests of the shelter	Update after every Insert operation (Animal > List Available will be needed when clients are added in a later sprint). May be a label or similar widget in the data area of the main window
SAVE	12	3		8			Manager	Save the data to a default file (File > Save)	Persist our data through the years	Requires Animal.save(bw), Dog.save, Cat.save, Shelter.save; Shelter.filename with getter and setter, and Mass.onSaveClick
LOAD	13	3		8			Manager	Load the data from a default file (File > Open)	Persist our data through the years	Requires Animal.Animal(br), Dog.Dog, Cat.Cat, Shelter.Shelter and Mass.onOpenClick; dialog and logic for handling “dirty” data
NEW	14	3		5			Director	Create a new shelter (File > New)	Open additional shelters as needed	Requires Mass.onNewShelterClick
SAVEF	15	3		5			Director	Save the data to a specified file (File > Save As)	Backup or baseline a new shelter	Requires Mass.onSaveAsClick, Shelter.setFilename; adding JFileChooser
LOADF	16	3		3			Director	Load the data from a specified file (File > Open)	Work with multiple shelters	Requires adding JFileChooser
GENERIC	17	4		13	5	In Work	Staff	Refactor Add (Animal) dialogs into generic class and add at least one additional family of animals	Quickly add additional animal families to our guest list	Requires generic class for unified dialog to create new animal guests
CLIENT	19	4		8	5	Finished in Sprint 5	Staff	Create a new client (Client > New)	Track candidate adopters	Requires Mass.onCreateClient; 1 dialog; class Client; Shelter.addClient and fields
LCLIENT	20	4		5	5	Finished in Sprint 5	Client	List clients (Client > List)	See which clients are available	Requires Shelter.numClients and client; and Mass.onClientsList
ITER	18	5		5				Refactor to use iterators to access animals from Shelter	Practice iterators (well?)	Replace numAnimals and getAnimal with getAnimalIterator; update all users of those methods
ADOPT	21	5		13			Client	Adopt an animal (Client > Adopt Animal)	Adopt an animal!	Requires Shelter.adopted HashMap<Animal, Client>, new dialog
LADOPT	22	5		8			Staff	List adopted animals (Client > List Adopted and Animal > List Adopted)	See which client adopted which animal	Requires 1 dialog to select the client and 1 dialog to select the animal; Mass.onListAdoptedClick

				Bonus Features
NANIM		4	TBD	5			Client	Create new animals and / or clients during adoption	Simplify the adoption process	Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
PHOTO		4	TBD	8			Client	See photo and information about an available animal	Decide if it’s right for my family	Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Feb 22		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 01		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Mar 01		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 08		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Mar 08		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 15		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Apr 12		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 19		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Apr 19		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 26		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	-2	2
Day 7 Left	-2	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CLIENT			Completed Day 6
2	LCLIENT			Completed Day 6
3	GENERIC			In Work
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84